## Risk Register
[22 empty] | H | Yes
[22 empty] | M | No
L
N/A
Project Risk Register
General Details | [5 empty] | Area of Impact |  |  | Exposure before Mitigation |  |  |  | Mitigation |  | Exposure after Mitigation
Risk Code | Date Logged | Category | Risk Description | Owner | Risk Status | Impact on Availability | Impact on Cost | Impact on solution Performance | Impact (1-10) 10=Major | Likelihood (1-10) 10=Certain | Used for Baseline Risk Graph only | Risk Rating (1-100) | Mitigation Strategy | Risk Closure Date | Impact (1-10) 10=Major | Likelihood (1-10) 10=Certain | Used for Current Risk Graph only | Risk Rating (1-100) | Date Last Updated | Comments
R1 | 2021-05-07 | Technical | Poor security configuration | IT Admin | #REF! | H | H | H | 10 | 8 | 108 | 80 | Transfer |  | 5 | 2 | 52 | 10 | 2021-05-14 | The IT admin need to use Amazon Elastic Compute Cloud (Amazon EC2) instance operating system Including patching, maintenance and firewall configuration according to the system complexity | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #REF! | #REF!
R3 | 2021-05-07 | Privacy Risk | CIA(Confidentiality Integrety Availibility) | IT Admin | #REF! | H | H | H | 8 | 9 |  | 72 | Mitigate |  | 1 | 2 |  | 2 | 2021-05-14 | Applications that are launched on AWS resources need to be secure that including security group configurations, firewall configurations, network configurations, and secure account management.
R5 | 2021-05-07 | Operational | Video Cameras | IT Admin | Open | M | L | H | 7 | 7 |  | 49 | Mitigate |  | 7 | 2 |  | 14 | 2021-05-14 | Prevent Cameras From Sending Information To Third Parties,including the camera manufacturer,assign IP address for each camera and subnet mask, and leave gateway blank or set to 127.0.0.1,
R6 | 2021-05-07 | Operational | Unplanned changes | Project Manager | Open | M | M | M | 7 | 5 |  | 35 | Avoid |  | 7 | 3 |  | 21 | 2021-05-14 | Have a clear agreed upon procedure to change the scope of work from the customer side.
R7 | 2021-05-07 | Operational | Cyber security incident | IT Admin | Open | H | M | M | 8 | 6 |  | 48 | Mitigate |  | 7 | 2 |  | 14 | 2021-05-14 | Create a policy by grant only the minimal user privileges needed to the user,secure Wi-Fi Network,replace outdated routers and
R8 | 2021-05-07 | Implementational | Delays in data migration from premises to AWS | Project Manager | #REF! | H | M | M | 8 | 9 |  | 72 | Mitigate |  | 6 | 5 |  | 30 | 2021-05-14 | Plan a head with the IT department so they will make sure that all storage devices in the company are ready on time
Note on M7: Valid values are 1 - 10. 1 - 4=Green 5 - 7=Yellow 8 - 10=Red
Note on V7: Enter any relevant comments. For example if the Risk becomes an Issue, enter it on the Issues Log and record the Issue Number here.

## Sheet1
Transfer
Avoid
Mitigate

## Risk Summary
Summary of Open Risks by Risk Owner | [7 empty] | Risk Owner Distribution
Owner | No. of Open Risks | Total Exposure |  | No. of Open Risks with Cutover Date in the next 30 days | No. of Open Risks with Cutover Date in the next 31-60 days | No. of Closed Risks | No. of Open Risks where Mitigation is in progress
|  | Before Mitigation | After Mitigation | [5 empty] | Total No. of Risks
Safety Engineer | 8 | 0 | 0 | 0 | 0 | 1 | 7
ADMIN | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 16
Project Manager | 2 | 0 | 0 | 0 | 0 | 0 | 2
Maintenance Engineer | 1 | 0 | 0 | 0 | 0 | 0 | 1
MR | 2 | 0 | 0 | 0 | 0 | 0 | 2
Procurement Engineer | 2 | 0 | 0 | 0 | 0 | 0 | 2
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 | Risk Summary
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 |  | Open Risks | 16
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 |  | Mitigation in Progress | 15
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0 |  | Closed Risk | 1
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 | 0 |  | 0
Total: | 16 | 0 | 0 | 0 | 0 |  | 15

## Formulae (hidden)
0 | 0 | 0 | 0 | 0 | #REF! | 356 | 0 | 0 | #REF! | 0 | 4 | 2 | 3
0 | 0 | 0 | 0 | 0 | #REF! | 91 | 0 | 0 | #REF! | 0 | 2 | 3 | 3
0 | 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 |  | 0 | 0 | 1 | 0
| 0 | 0 | 0 | 0 | #REF! |  | 0 | 0 |  | 0 | 6 | 6 | 6
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0
| 0 | 0 | 0 | 0 |  |  | 0 | 0 |  | 0